| Company Name | Lump Sum Bid | Comments |
| --- | --- | --- |
| Anlaan Corporation 16750 Lincoln Street Grand Haven, MI 49417 | $263,000.00 | Delivery time of materials may run past Completion date. |
| C.A. Hull 8177 Goldie Street Commerce Township, MI 48390 | $198,950.00 | Note change in completion date. |
| Heavy Structural Preservation 3998 M-72 Alpena, MI 49707 | $148,900.00 |  |
| John Henry Inc. 1140 Henry Road East Tawas, MI 48730 | $139,000.00 | Material may not be available until 2027 Winter work complicates water barrier and paving |
| RCL Construction 777 W. Maynard Road Sanford, MI 48657 | $199,300.00 | Lead-times on Timber materials, including shop drawings are 24 weeks. Falls outside completion window. |
| Schepke Consulting 101 Ballard St. Roscommon, MI 48653 | $105,000.00 |  |
| Tim & Sons Construction LLC. 22689 Junction Rd Bellevue, MI 49021 | $137,248.00 |  |

Steckert Bridge Repair 2026 Bid Tab